## Summary
Initiative | Install Kanban Task Board | [5 empty] | Status | 4-Success Map tracking |  | Last Update | 2018-12-12 |  | Update Due
Guide (Sponsor) |  |  | Action Plan
Sponsor |  | Hannah | Deliverable |  |  |  | Next Action |  |  | Date | Owner | Plan | Replan | Fcst | Actual
|  |  | Define standard work for Kanban | [7 empty] | BB | 2019-11-22 |  | 2019-11-22
Explain Need |  | Our team brings in a large number of small- and medium-sized tasks with no structured means to prioritize. This leads to systematic oversubscription, frustrating the team and disappointing internal customers | Pilot 1 | [7 empty] | Tucker | 2019-11-29 |  | 2019-11-29
|  |  | Pilot 2 | [7 empty] | Tucker | 2019-12-06 |  | 2019-12-06
|  |  | Train team | [7 empty] | BB | 2019-12-13 |  | 2019-12-13
|  |  | Define standard work for collecting rev by task | [7 empty] | BB | 2019-12-27 |  | 2019-12-27
Need-by date |  | 2 months fully installed | Buffer | [8 empty] | 2019-12-27 |  | 2019-12-27
Owner name |  | Tucker
Team members |  | BB Johnson, Urs, Diego, Eyal
Focus
Problem or Opportunity |  | Create global, single point of truth for task acceptance, prioritized by internal customers
Test Track
Metric |  | On-schedule delivery, realized value
|  |  | Case |  | Dates | Meeting Held |  | All Projects Complete |  | All Projects report rev. |  | -- |  | --
Current Perf. |  | Unknown | 1st Meeting (12/15) |  | Plan | 2019-05-01 |  | 2019-05-15 |  | 2019-05-22
Replan
Forecast
Targert Perf. |  | 90% on schedule, generating $2M revenue/year |  |  | Actual
|  |  | 2nd Meeting (12/18) |  | Plan | 2019-05-11 |  | 2019-05-25 |  | 2019-06-01
Replan
Solve Method |  | Virtual event with full team, 2-3 hours per day, 5-6 meetings over 2 weeks. |  |  | Forecast
Actual
Solve |  |  | 3rd Meeting (1/2) |  | Plan | 2019-05-19 |  | 2019-06-02 |  | 2019-06-09
Replan
Root Cause |  | No standardized means to review and prioritize/rationalize tasks. No standard measures of value. |  |  | Forecast
Actual
|  |  | -- |  | Plan
Replan
Forecast
Solution |  | Install electronic Kanban board for tasks taken by global team; track value delivered annually |  |  | Actual
Bowlers
|  |  | Goal 1 | Tasks completed to schedule
Counter Measures | 1 | Install electronic Kanban | Date | 2019-01-01 | 2019-02-01 | 2019-03-01 | 2019-04-01 | 2019-05-01 | 2019-06-01 | 2019-07-01 | 2019-08-01 | 2019-09-01 | 2019-10-01 | 2019-11-01 | 2019-12-01
|  |  | Plan | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90%
Replan
Fcst
| 2 | Hold bi-weekly meetings to prioritize new tasks and review old tasks | Act
|  |  | Goal 2 | Revenue earned throughout year
|  |  | Date | 2019-01-01 | 2019-02-01 | 2019-03-01 | 2019-04-01 | 2019-05-01 | 2019-06-01 | 2019-07-01 | 2019-08-01 | 2019-09-01 | 2019-10-01 | 2019-11-01 | 2019-12-01
| 3 | Report value delivered by Kanban projects | Plan | 166.6667 | 333.3333 | 500 | 666.6667 | 833.3333 | 1000 | 1166.6667 | 1333.3333 | 1500 | 1666.6667 | 1833.3333 | 2000
Replan
Forecast
Actual
Formulas:
Plan = DATE(YEAR([Owner]),MONTH([Owner])+IF('Success Map'!$J46='Success Map'!$R44,'Success Map'!$I46,0),DAY([Owner])+IF('Success Map'!$J46<>'Success Map'!$R44,'Success Map'!$I46,0))
Owner = DATE(YEAR([Last Update]),MONTH([Last Update])+IF('Success Map'!$J46='Success Map'!$R44,'Success Map'!$I46,0),DAY([Last Update])+IF('Success Map'!$J46<>'Success Map'!$R44,'Success Map'!$I46,0))
Update Due = DATE(YEAR([Plan]),MONTH([Plan])+IF('Success Map'!$J46='Success Map'!$R44,'Success Map'!$I46,0),DAY([Plan])+IF('Success Map'!$J46<>'Success Map'!$R44,'Success Map'!$I46,0))
Fcst = DATE(YEAR([Update Due]),MONTH([Update Due])+IF('Success Map'!$J46='Success Map'!$R44,'Success Map'!$I46,0),DAY([Update Due])+IF('Success Map'!$J46<>'Success Map'!$R44,'Success Map'!$I46,0))
Actual = DATE(YEAR([Fcst]),MONTH([Fcst])+IF('Success Map'!$J46='Success Map'!$R44,'Success Map'!$I46,0),DAY([Fcst])+IF('Success Map'!$J46<>'Success Map'!$R44,'Success Map'!$I46,0))

## Success Map
Summary Instructions | [14 empty] | 1-New | 4
2-Rdy for Pblm
The success map planning is filled in immediately after a problem solve. The Success Map may not be changed unless renegotiated with the sponsor | [14 empty] | 3-Rdy to Solve
4-Success Map tracking
Values entered here are automatically copied to the Main page of this canvas for tracking
If a Stop-Fix alarm occurs, the team is expected to take all practical steps to protect the dates and goals before starting to renegotiate the plan
A. Action Plan Instructions |  |  |  | Action Plan--Plannning Data | [8 empty] | Start Date
2019-11-01
1. Divide the initiative in about 10 steps, roughly equal in complexty. |  |  |  | Deliverable |  |  |  | Owner | # weeks, normal | # weeks, compress (calc) | # weeks, compress | Internal Plan | Plan
2. Define a measurable deliverable due at each step. |  |  |  | Define standard work for Kanban |  |  |  | BB | 3 | 2.4 | 2.4 | 2019-11-17 19:12 | 2019-11-22
|  |  |  | Pilot 1 |  |  |  | Tucker | 1 | 0.8 | 0.8 | 2019-11-23 09:36 | 2019-11-29
3. Estimate the time to complete each step under "normal" circumstances |  |  |  | Pilot 2 |  |  |  | Tucker | 1 | 0.8 | 0.8 | 2019-11-29 | 2019-12-06
|  |  |  | Train team |  |  |  | BB | 1 | 0.8 | 0.8 | 2019-12-04 14:24 | 2019-12-13
4. Compress each step, on average, about 20% to take out the buffer we automatically insert when estimating "normal" time. |  |  |  | Define standard work for collecting rev by task |  |  |  | BB | 2 | 1.6 | 1.6 | 2019-12-15 19:12 | 2019-12-27
|  |  |  | Buffer | [6 empty] | 1.6 | 2019-12-27 | 2019-12-27
5. A standard compression is calculated (20%) as a reference
6. The team should select the actual compressed estimations they can commit to.
7. Throughout the tracking process, you can use up to a specific amount of buffer to turn off Stop-Fix alarm.
[9 empty] | 8 | 6.4 | 8
B. Test Track Plan |  | Test Track--Planning Data
1. Identify 3-4 cases the team will follow closely to "watch it work" |  | Case |  | Meeting Held |  | All Projects Complete |  | All Projects report rev.
|  | 1st Meeting (12/15) |  | 2019-12-15 |  | 2019-01-22 |  | 2019-01-25
2. Divide "watch it work" into 3-5 makor "Laps" |  | 2nd Meeting (12/18) |  | 2019-12-18 |  | 2019-01-26 |  | 2019-01-29
|  | 3rd Meeting (1/2) |  | 2019-01-02 |  | 2019-01-31 |  | 2019-02-03
3. Rename Laps row, e.g., change "Lap 1" to "First prototype ship"
4. Plan out when each of the "Cases" will complete each "Lap"
C. Bowler Plan | Bowler--Planning Data | [12 empty] | Month(s)
Day(s)
1. Fill in Goal 1 and, optionally Goal 2 | Start on: | 2019-01-01 |  | Cadence | 1 | Month(s)
| Goal 1 | Tasks completed to schedule
2. Select the date to start on. | Date | 2019-01-01 | 2019-02-01 | 2019-03-01 | 2019-04-01 | 2019-05-01 | 2019-06-01 | 2019-07-01 | 2019-08-01 | 2019-09-01 | 2019-10-01 | 2019-11-01 | 2019-12-01
| Plan | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90%
3. Select Cadence = time duration of each column
| Goal 2 | Revenue earned throughout year
4. Select Cadence units, either days or months | Date | 2019-01-01 | 2019-02-01 | 2019-03-01 | 2019-04-01 | 2019-05-01 | 2019-06-01 | 2019-07-01 | 2019-08-01 | 2019-09-01 | 2019-10-01 | 2019-11-01 | 2019-12-01
| Plan | 166.6667 | 333.3333 | 500 | 666.6667 | 833.3333 | 1000 | 1166.6667 | 1333.3333 | 1500 | 1666.6667 | 1833.3333 | 2000
5. Fill in "favorability for each goal. "Positive Favorable" is goals we are maximizing (like Revenue). An example of "Neg. Favorable" Cost. | [10 empty] | Goal 1 Favorability |  |  | Pos
[11 empty] | Goal 2 Favorability |  |  | Neg
6. Fill in plan for each applicable column
What to do in a Stop-Fix alarm
It almost always happens that unexpected events make staying out of Stop-Fix alarms more difficult than anticipated. There are three responses
Formulas:
Start Date = IF([Action Plan--Plannning Data]="","",Q11+M14*7)
Start Date = IF([Action Plan--Plannning Data]="","",[Start Date, row above]+M15*7)